FRESH ROADMAP

AI Security + Business CRM SaaS — Current State to Final Certification

Baseline: 13 September 2026. This is the forward execution roadmap. Historical plans remain evidence, but completed historical phases must not be replayed.

# 1. Executive Direction

The project is on the correct architectural path. The product is an AI Security + Business CRM SaaS with isolated customer deployments: one codebase, separate environment/infrastructure/credentials per customer company. Platform subscription billing/payment processing is deprecated; business revenue, products, pricing, quotations, approvals and reporting remain.

Planning estimate at this checkpoint: engineering/platform foundation ~80–85%; complete product functionality ~62–67%; production-certified confidence ~35–40%. These are planning estimates, not KPIs.

# 2. Non-Negotiable Rules

Evidence beats assumptions; actual source and executable tests beat stale documentation.

Never restart completed work. Reconcile every old OPEN item against the repository first.

Never request, print, commit or expose credentials/secrets. Missing optional providers must degrade explicitly; never fake success.

Production is read-only unless explicitly authorized. No destructive SQL, reset, migration experimentation or credential rotation without authorization.

Never claim full-suite PASS while inherited failures remain. Classify PASS / FAIL / BLOCKED / KNOWN INHERITED FAILURE.

Server authorization is authoritative; UI checks are UX only. Preserve tenant isolation, RBAC, soft-delete, auditability, idempotency and ownership.

Do not add schema changes unless genuinely required. Never use destructive git cleanup such as git clean -fd or git reset --hard without authorization.

Every phase ends with focused tests, relevant broader tests, TypeScript/Prisma/lint as applicable, diff review and explicit production status.

# 3. Architectural Baseline

| Area | Current direction | Forward rule |
| --- | --- | --- |
| Deployment | Separate isolated deployment/environment/infrastructure/credentials per company | Configuration-driven provisioning; no business-logic forks. |
| Tenant security | Application authorization + tenant context + PostgreSQL RLS | Never rely on one layer alone. |
| DB roles | crm_app_user: NOBYPASSRLS; crm_system_user: BYPASSRLS; neither owns app tables | Keep app/system boundaries explicit. |
| AI | Real Gemini provider abstraction, controlled tools, safe degradation | No fake inference; audit tool actions. |
| Realtime | Pusher-oriented abstraction; CallSession; server-relayed WebRTC signaling | Real provider/browser E2E still required. |
| CCTV | MediaMTX + durable worker + object storage | No persistent CCTV worker/filesystem work in serverless routes. |
| Storage | S3-compatible provider + signed URLs | Real isolated object storage for production. |
| Billing | No platform subscription/payment processing | Retain business revenue capabilities. |

# 4. Already Substantially Complete — Do Not Rebuild

Canonical migration/baseline and production reconciliation work.

Core CRM customer/contact/lead/pipeline/deal lifecycle, including contact update/archive and deal update/archive.

Customer 360 timeline and mobile UX.

R.14.6 security/completeness hardening; 28/28 focused tests pass.

CCTV R01–R09 security hardening; secure WHEP/webhook/path/recording controls; S3 signed recording playback.

AI Gemini provider boundary, safe degradation and authorization-aware tool foundations.

CallSession, concurrency protection, server-relayed WebRTC signaling and browser WebRTC hook.

Reporting date filtering, domain reports, exports, drill-downs and security/tenant checks.

Demo provisioning safety and provider failure/idempotency patterns.

# 5. Known Limitations / Blockers

Historical full-suite DR timeouts remain unless newly resolved: global retention discovery and global RPO inspection in dr-remediation.test.ts.

Real browser-to-browser WebRTC E2E requires isolated real Pusher infrastructure/credentials and browser media/dual-auth setup.

CCTV real operational E2E requires legitimate MediaMTX, RTSP camera, browser WebRTC and isolated object-storage infrastructure.

AI production behavior depends on legitimate provider credentials; missing credentials must degrade safely.

Production confidence remains below code maturity because real infrastructure, DR, load, provisioning and operational evidence remain.

# 6. PHASE 0 — Fresh Reconciliation Gate

Inspect git branch, HEAD, origin/main and working tree.

Read latest handovers, progress, roadmap and credential-handling documents.

Build a live capability matrix: feature, implementation, tests, production evidence, blocker, remaining work.

Reconcile every historical OPEN item against source/tests.

Inventory schema/migration state and provider readiness.

Select the next phase by security risk, user value, dependencies and production-readiness impact.

Exit: current-state matrix is documented and the next phase has explicit acceptance criteria.

# 7. PHASE 1 — Workforce / Organization / Employee Completion

Complete company → department → head → employee structure.

Complete invitations/onboarding using existing auth boundaries.

Complete role/permission assignment and server enforcement.

Guarantee company boundaries and safe deactivation/archive semantics.

Integrate employees with internal calling/messaging/presence.

Audit invitations, role changes and lifecycle events.

Add negative authorization and cross-tenant tests.

# 8. PHASE 2 — Communication Completion

Complete internal messaging UI/persistence and unified inbox/thread/history.

Complete customer/contact communication timeline.

Complete email/SMS/external adapters where configured.

Implement provider readiness/failure, retry and idempotency behavior.

Complete attachments and security limits.

Complete presence/notifications through realtime abstraction.

Test authorization, tenant isolation, duplicates, retries and provider outages.

# 9. PHASE 3 — Realtime + Internal Calling

Complete private-channel authorization and tenant/user channel naming.

Verify complete CallSession lifecycle and terminal-state protection.

Verify one-active-call race protection.

Complete browser media, peer lifecycle, cleanup and failure handling.

Create isolated real Pusher E2E environment when credentials are legitimately available.

Run dual-user browser E2E; verify signaling, CallLog linkage, permissions and outage behavior.

# 10. PHASE 4 — CCTV Operational Completion

Provision real MediaMTX per isolated deployment.

Connect legitimate RTSP/RTSPS camera source.

Verify SSRF/credential protection and opaque path/JWT/WHEP flow.

Verify recording daemon, leases, fencing, stale recovery and node affinity.

Verify real S3/R2/MinIO-compatible upload and signed playback/download.

Verify retention and deletion semantics.

Verify webhook authentication, nonce/idempotency and replay protection.

Verify events/incidents/alerts/audit.

Enable CCTV AI only after real infrastructure is proven.

# 11. PHASE 5 — AI Assistant + Security Intelligence

Complete controlled tool registry and per-tool authorization.

Complete CRM/security summaries and reporting assistance.

Make privileged/approval-sensitive actions explicitly gated.

Audit AI actions/tool calls without unnecessary prompt/PII logging.

Complete prompt-injection boundaries and negative tests.

Implement provider timeout/retry/error/degradation.

Complete CCTV AI jobs/events where infrastructure exists.

Verify cost precision and secret protection.

# 12. PHASE 6 — Revenue / Quotes / Approvals

Complete products, pricing and price-book lifecycle.

Complete quotations and quote versions.

Complete discounts and approvals.

Complete revenue reporting.

Preserve Decimal(19,4) commercial money and Decimal(19,8) AI provider cost, HALF_UP, 2-decimal display.

Do not convert Deal.value merely for consistency.

Test authorization, audit, tenant isolation, lifecycle and approval concurrency.

# 13. PHASE 7 — Reporting / Analytics Finalization

Complete required CRM/sales/security/communication reports.

Keep date filtering server-enforced.

Complete authorized bounded exports and drill-downs.

Complete useful domain filters.

Validate tenant/RBAC enforcement.

Validate realistic large datasets and aggregation performance.

Remove remaining fake/simulated reporting states.

# 14. PHASE 8 — Notifications / Workflow / Background Processing

Complete notification lifecycle and preferences.

Complete authenticated outbox processing.

Verify retries, backoff and dead-letter behavior where applicable.

Verify idempotency and duplicate suppression.

Verify worker leases, stale recovery and concurrency fences.

Add queue/worker latency, failure and retry observability.

Test multi-tenant worker isolation.

# 15. PHASE 9 — Enterprise Security Hardening

Run complete authorization matrix.

Run cross-tenant adversarial tests across CRM, communication, CCTV, AI, reports and workforce.

Audit raw SQL for parameterization and justified system-only use.

Verify RLS/application authorization alignment.

Verify append-only AuditLog.

Verify encrypted/isolated credentials and log redaction.

Verify SSRF, file/path and symlink boundaries.

Verify rate/request-size/abuse controls where applicable.

Verify safe defaults for missing providers.

# 16. PHASE 10 — Observability + DR

Resolve or certify inherited DR failures.

Document backups, frequency, retention and integrity.

Perform isolated restore drills.

Measure RPO and RTO.

Verify application/workers/queues after recovery.

Verify tenant isolation after restore.

Verify retention/deletion after restore.

Create runbooks for provider outage, DB recovery, worker failure, CCTV node failure and credential rotation.

Add production-grade health/metrics/alerts.

# 17. PHASE 11 — Scale / Concurrency / Load

Define target concurrency per isolated company.

Load-test auth, CRM, communication/outbox, CallSession/signaling, CCTV ingestion and reporting.

Test DB connections/pooling.

Test duplicate worker delivery and idempotency.

Measure p50/p95/p99 latency, throughput and errors.

Fix evidence-backed bottlenecks.

Repeat security tests after performance changes.

# 18. PHASE 12 — Repeatable Customer Provisioning

Create deterministic new-company provisioning.

Provision isolated deployment/environment/database/auth/providers.

Apply canonical baseline/migrations.

Create required roles and initial administrator safely.

Configure optional providers without requiring them.

Run health, tenant-isolation and representative capability smoke tests.

Produce machine-readable/customer-facing certification evidence.

Ensure no business-logic code fork is required.

# 19. PHASE 13 — Production Certification

Read-only structural/schema/migration checks.

Role/RLS/native-object fingerprints.

Health and authentication/authorization smoke tests.

Provider readiness verification.

Safe critical workflow checks.

Observability/alerting verification.

Backup/DR evidence.

Security evidence.

Confirm no production mocks/placeholders/fake success.

Document all residual limitations.

# 20. PHASE 14 — Final Product Certification / Release Gate

Core CRM certified.

Communication/calling/email/SMS certified according to configured providers.

CCTV real E2E certified where deployed.

AI certified with real provider or safely disabled.

Realtime certified where enabled.

Employees/departments/roles/onboarding certified.

Revenue/quotes/approvals/reporting certified.

Tenant/security/RBAC/RLS certified.

Workers/queues/retry/idempotency certified.

Observability/DR/RPO/RTO certified.

Scale/concurrency evidence recorded.

Customer-isolated provisioning certified.

Security audit clean or residual risks explicitly accepted.

Final production smoke test passes.

Release and customer handoff documentation complete.

# 21. Definition of Done — Whole Product

Every promised capability has a real implementation or explicit disabled/unavailable state.

Security-sensitive capabilities have negative-path tests.

Tenant-sensitive capabilities have cross-tenant tests.

External providers have explicit readiness/failure semantics.

No production path uses fake success.

Workers/queues have retry, idempotency and concurrency evidence.

CCTV, AI and realtime have real infrastructure evidence where enabled.

DR has demonstrated restore and measured RPO/RTO.

Scale/concurrency behavior is measured.

New customer provisioning is repeatable.

Production certification is deployment-specific and evidence-based.

Documentation matches the repository.

# 22. Execution Protocol for Every Phase

Audit current state.

Write acceptance criteria.

Inspect existing architecture.

Implement smallest complete change.

Add focused security/functional tests.

Run focused tests.

Run TypeScript/Prisma/relevant lint.

Run broader relevant suites.

Inspect diff and git status.

Document blockers and production status.

Commit only intentional changes according to workflow.

Update live roadmap/status matrix before selecting the next phase.

# 23. Credential Handling

Use legitimate credentials only in intended secret stores/environments.

Never paste secrets into chat or documentation.

Never commit credentials.

Never fabricate credentials or provider success.

Classify provider readiness as READY / MISSING_CREDENTIALS / MISCONFIGURED / UNAVAILABLE as appropriate.

Optional providers degrade safely; critical providers fail explicitly.

Each customer deployment receives its own provider credentials and isolation.

# 24. Final Progress Dashboard

| Capability | Current direction | Final evidence |
| --- | --- | --- |
| Core CRM | Substantially complete | Integration + production smoke |
| Workforce | Remaining | Real onboarding/RBAC/company flow |
| Communication | Partial/substantial | Provider + retry/idempotency evidence |
| Realtime/calling | Partial/substantial | Real provider + dual-browser E2E |
| CCTV | Strong foundation | Real camera/MediaMTX/worker/storage E2E |
| AI | Foundation | Real provider + tool/RBAC/audit E2E |
| Revenue/quotes | Substantial | Lifecycle/approval/security evidence |
| Reporting | Substantial | Large-data/security/export evidence |
| Workers/queues | Partial/substantial | Concurrency/failure evidence |
| Observability | Partial | Production metrics/alerts/runbooks |
| DR | Partial | Restore + RPO/RTO |
| Scale | Partial | Load/concurrency certification |
| Provisioning | Partial | Repeatable isolated deployment certification |
| Production certification | Not complete | Deployment-specific final evidence |

# 25. Strategic End State

The finish line is not a number of screens, files, commits or roadmap checkboxes. The product is finished when its intended capabilities are usable, secure, tenant-isolated, observable, recoverable, scalable and proven against the real infrastructure they depend on.

The forward strategy is therefore: reconcile → prioritize genuine gaps → implement → adversarial test → verify integrations → certify operations → certify isolated customer provisioning → certify production → release.

This roadmap intentionally preserves the project's security-first and evidence-first direction while replacing stale historical sequencing with a live, capability-based execution model.